## Table 1
Rehab/Construction Budget
Property Address:
Draw Requests
| Line Items | Description of item, labor, material, location, brands, etc… | Estimated Cost | Actual Budget/Cost | Draw 1- Requested 1/2/2018 | Draw 2- Requested 2/2/2018 | Draw 3- Requested 3/15/2018 | Draw+ | % of Budget | Status
GENERAL
Exact Same | Architect Fees |  | 3000 |  | 3000
NEW | Engineer Fees | [7 empty] | 100% | Finished
Relabel | Permit Fees |  | 1800 |  | 500 | 500 |  |  | 90% | Not Started
NEW | Site Setup | [8 empty] | In Progress
NEW | Survey |  | 450 |  | 450 |  |  |  |  | Pending Inspection
NEW | Dumspters |  | 1500 |  |  | 700
NEW | Mold Inspection/Remediation | [8 empty] | Finished
Exact Same | Termite Inspection/Treatment
New | Staging
Relabel | Foundation Inspection/Repairs
Relabel | Structural Inspection/Repairs
NEW | Cost Overun Reserve |  | 10000
NEW | Other+
Interior
Relabel | Demolition |  | 1000 |  | 1000
Relabel | Paint |  | 5000 |  |  |  | 4500
Relabel & Merge | Flooring | doing 5000 sq ft total- 2500 marble & 2500 wood | 40000 |  |  | 20000 | 20000
Same | Doors |  | 1800 |  |  |  | 1800
Same | HVAC Rough |  | 5000 |  | 5000
Relabel | HVAC Install/Repairs
Same | Eletrical-Rough |  | 3500 |  | 3500
Relabel | Eletrical-Finish/Fixtures |  | 2500 |  |  |  | 2500
Same | Plumbing-Rough |  | 2500 |  | 2500
Same | Plumbing-Finish/Fixtures |  | 2500 |  |  | 2500
Same | Kitchen Cabinets |  | 12000 |  |  | 8500
Same | Kitchen Counters |  | 4000 |  |  | 4000
Same | Appliances |  | 1200 |  |  | 1200
Same | Bath 1 |  | 5000 |  |  |  | 4500
Same | Bath 2
Same | Bath 3
Relabel "Sheet Rock" | Framing/ Drywall |  | 2500
NEW | Trim/Mouldings/Baseboard |  | 600
New | Closets |  | 6000
NEW | Stairs
NEW | Audio/Visual |  | 2000 |  | 2000
NEW | Custom Work
NEW | Other+
EXTERIOR
NEW | New Addition/Shell
New | Exterior Paint |  | 4000 |  |  |  | 4000
New | Stucco |  | 1500 |  | 1500
Same | Windows
Same | Doors |  | 1000 |  |  | 1000
Relabel "Siding" | Siding/Trim
Same | Roofing |  | 2500 |  | 2500
Same | Landscape |  | 2000 |  |  |  | 2000
NEW | Fencing/Gates
New | Garage
Relabel "deck/Porch" | Decks & Patios
Relabel "Driveway, Walkway, Patio" | Driveway/Walkway
New | Pool/Waterscape |  | 25000 |  | 24000
New | Irrigation
New | Well
New | Septic
New | Other+
| Total |  | 133100 |  | 42000 | 37200 | 39300
| Status on Draw |  |  |  | Draw Disbursed | Pending Inspection
| Over/Under Budget & Current Escrow Available |  | 14600
| Overall % Complete |  | -89.0308
| Total Draws |  | 118500
| Initial Loan Amount Funded |  | 400000
| Total Current Balance |  | 518500
Note on K4: Chris Fuelling: Add values: Not Started, 25% Complete, 50% Complete, 75% Compete, Finished, In Progress, Pending Inspection, Needs Budget Approval, Canceled,
Note on B11: Chris Fuelling: Currently we have Demolition/trash/dumpsters… create new dumspter line item
Note on B18: Chris Fuelling: Can we allow user to create new line items?
Note on B23: Chris Fuelling: Currently we have 3 sub fields here- Carpet/Vinyl, Tile, Hardwood… You can consolidate all 3 into one field.